## user guide
Gantt Chart Template Antonio López Rivera, 2025 With automatic: • Gantt chart plot based on task dates • Delay highlighting • Task classification hierarchy • Month labelling
User Guide Project duration Start date to end date. Task hierarchy Derived from task code. |  |  |  | Tip Tables Generator Export the Gantt chart to LaTeX at: • https://www.tablesgenerator.com
Milestones • Code: no code • Color: light blue |  | Blocks • Code: no period • Color: blue |  | Tasks • Code: one period • Color: orange |  | Subtasks • Code: two periods • Color: grey
| MILESTONE | 1 | Block | 1.1 | Task | 1.1.1 | Subtask
Details • Automatic Gantt chart plotting based on task dates (formula) • Calendar rendering based on ISO week number • Automatically generated date range from project start to end date (SEQUENCE of ISO week numbers) • Automatically generated month labelling (formula) • Automatically highlighting (conditional formatting rules)

## example
|  | Start date | 2025-02-01
|  | End date | 2025-10-31
[10 empty] | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43
MSc THESIS PLAN | TASK |  | DAYS EXPECTED |  | DAYS DONE |  | BUDGET DEVIATION | START | END | 5: CALENDAR
[10 empty] | FEB |  |  |  | MAR |  |  |  |  | APR |  |  |  | MAY |  |  |  | JUN |  |  |  |  | JUL |  |  |  | AUG |  |  |  | SEP |  |  |  |  | OCT
|  | MILESONE: PROJECT PROPOSAL APPROVAL | [5 empty] | 2025-02-15 | 2025-02-15 | 7: 0
| 1 | Impulsive Trajectory Design | 7 |  | 10 |  | 42.86% | 2025-02-15 | 2025-02-25 | bar: 7 to 9
| 1.1 | Multiple Hohmann transfers | 5 |  | 7 |  | 40% | 2025-02-15 | 2025-02-22 | 7: 2; 8: 2
| 1.2 | Impulsive plane change manoeuvres | 2 |  | 3 |  | 50% | 2025-02-22 | 2025-02-25 | 8: 2; 9: 2
| 2 | Low-Thrust Trajectory Design | 21 |  | 65 |  | 209.5% | 2025-02-15 | 2025-04-21 | bar: 7 to 17
| 2.1 | LTTO approach trade-off | 5 |  | 10 |  | 100% | 2025-02-15 | 2025-02-25 | 7: 2; 8: 2; 9: -1
| 2.2 | Q-Law | 12 |  | 51 |  | 325% | 2025-02-25 | 2025-04-17 | 9: 2; 10: 2; 11: -1; 12: -1; 13: -1; 14: -1; 15: -1; 16: -1
| 2.2.1 | Guidance law |  | 10 |  | 21 | 110% | 2025-02-25 | 2025-03-18 | 9: 3; 10: 3; 11: -1; 12: -1
| 2.2.2 | Trajectory generation |  | 0 |  | 8 | Unacc. | 2025-03-18 | 2025-03-26 | bar: 12 to 13
| 2.2.3 | Verification |  | 0 |  | 15 | Unacc. | 2025-03-26 | 2025-04-10 | bar: 13 to 15
| 2.2.4 | Integrator selection |  | 0 |  | 2 | Unacc. | 2025-04-10 | 2025-04-12 | bar: 15
| 2.2.5 | Transfer cost estimation |  | 2 |  | 5 | 150% | 2025-04-12 | 2025-04-17 | 15: 3; 16: 3
| 2.3 | RQ-Law | 4 |  | 4 |  | 0% | 2025-03-17 | 2025-04-18 | 12: 2; 13: -1; 14: -1; 15: -1; 16: -1
| 2.3.1 | Guidance law |  | 2 |  | 2 | 0% | 2025-03-17 | 2025-03-19 | 12: 3
| 2.3.2 | Transfer cost estimation |  | 2 |  | 2 | 0% | 2025-04-17 | 2025-04-19 | 16: 3
| 3 | Approximate Solutions | 8.5 |  | 15 |  | 76.47% | 2025-03-15 | 2025-04-01 | bar: 11 to 14
| 3.1 | RAAN walk | 0.5 |  | 1 |  | 100% | 2025-03-15 | 2025-03-16 | 11: 2
| 3.2 | Dynamic RAAN nearest-neighbor search | 3 |  | 7 |  | 133.3% | 2025-03-16 | 2025-03-23 | 11: 2; 12: 2
| 3.3 | Dynamic Beam Search | 5 |  | 7 |  | 40% | 2025-03-23 | 2025-03-30 | 12: 2; 13: 2
| 4 | Heuristic Combinatorial Optimization | 14 |  | 36 |  | 157.1% | 2025-04-01 | 2024-05-12 | bar: 14 to 19
| 4.1 | Dynamic environment modelling | 2 |  | 2 |  | 0% | 2025-04-01 | 2025-04-03 | 14: 2
| 4.2 | Population Sampling | 4 |  | 18 |  | 350% | 2025-04-03 | 2025-04-21 | 14: 2; 15: 2; 16: -1; 17: -1
| 4.2.1 | Uniform permutation sampling |  | 2 |  | 8 | 300% | 2025-04-03 | 2025-04-11 | 14: 3; 15: -1
| 4.2.2 | Distance-based permutation sampling |  | 2 |  | 10 | 400% | 2025-04-11 | 2025-04-21 | 15: 3; 16: -1; 17: -1
| 4.3 | Population encoding | 1 |  | 2 |  | 100% | 2025-04-21 | 2025-04-23 | 17: 2
| 4.4 | Optimizer trade-off | 7 |  | 14 |  | 100% | 2025-04-23 | 2025-05-07 | 17: 2; 18: 2; 19: -1
|  | MILESONE: MIDTERM REVIEW | [5 empty] | 2025-05-13 | 2025-05-13 | 20: 0
| 5 | Neural Combinatorial Optimization | 48 |  |  |  |  | 2025-05-14 | 2025-07-01 | bar: 20 to 27
| 6 | Integration of SCP | 21 |  |  |  |  | 2025-06-24 | 2025-07-15 | bar: 26 to 29
| 7 | Study of STSP Variants | 14 |  |  |  |  | 2025-07-01 | 2025-07-15 | bar: 27 to 29
| 8 | Writing | 48 |  |  |  |  | 2025-06-15 | 2025-08-02 | bar: 24 to 31
|  | MILESONE: GREEN LIGHT MEETING | [5 empty] | 2025-08-03 | 2025-08-03 | 31: 0
|  | MILESONE: IAC 2024 PAPER DEADLINE | [5 empty] | 2025-08-21 | 2025-08-21 | 34: 0
|  | MILESONE: DEFENSE | [5 empty] | 2025-08-31 | 2025-08-31 | 35: 0
Formulas:
END = [START]+[DAYS DONE]
END = [START]+G14
START = [END, row above]
START = [START, row above]

## template
|  | Start date | 2025-02-01
|  | End date | 2025-10-31
[10 empty] | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43
Project Plan | TASK |  | DAYS EXPECTED |  | DAYS DONE |  | BUDGET DEVIATION | START | END | 5: CALENDAR
[10 empty] | FEB |  |  |  | MAR |  |  |  |  | APR |  |  |  | MAY |  |  |  | JUN |  |  |  |  | JUL |  |  |  | AUG |  |  |  | SEP |  |  |  |  | OCT
|  | MILESTONE 1 | [5 empty] | 2025-02-15 | 2025-02-15 | 7: 0
| 1 | Block 1 | 15 |  | 39 |  | 160% | 2025-02-15 | 2025-03-26 | bar: 7 to 13
| 1.1 | Task 1 | 5 |  | 10 |  | 100% | 2025-02-15 | 2025-02-25 | 7: 2; 8: 2; 9: -1
| 1.2 | Task 2 | 10 |  | 29 |  | 190% | 2025-02-25 | 2025-03-26 | 9: 2; 10: 2; 11: -1; 12: -1; 13: -1
| 1.2.1 | Subtask 2.1 |  | 10 |  | 21 | 110% | 2025-02-25 | 2025-03-18 | 9: 3; 10: 3; 11: -1; 12: -1
| 1.2.2 | … |  | 0 |  | 8 | Unacc. | 2025-03-18 | 2025-03-26 | bar: 12 to 13
| 2 | Block 2 | 0.5 |  | 1 |  | 100% | 2025-03-15 | 2025-04-01 | bar: 11 to 14
| 2.1 | … | 0.5 |  | 1 |  | 100% | 2025-03-15 | 2025-03-16 | 11: 2
|  | MILESTONE 2 | [5 empty] | 2025-05-13 | 2025-05-13 | 20: 0
| 3 | Block 3 | 48 |  |  |  |  | 2025-05-14 | 2025-07-01 | bar: 20 to 27
| 4 | Block 4 | 21 |  |  |  |  | 2025-06-24 | 2025-07-15 | bar: 26 to 29
| 5 | Block 5 | 14 |  |  |  |  | 2025-07-01 | 2025-07-15 | bar: 27 to 29
| 6 | Block 6 | 48 |  |  |  |  | 2025-06-15 | 2025-08-02 | bar: 24 to 31
|  | MILESTONE 2 | [5 empty] | 2025-08-03 | 2025-08-03 | 31: 0
|  | MILESTONE 3 | [5 empty] | 2025-08-21 | 2025-08-21 | 34: 0
|  | MILESTONE 4 | [5 empty] | 2025-08-31 | 2025-08-31 | 35: 0
Formulas:
END = [START]+[DAYS DONE]
END = [START]+G11
START = [END, row above]